## PDMaster
S.No | Proj. Ref. No. | Project | Location | Business | Category | Project Brief | Project Manager | Status | ACS Scope | VSS Scope | Other Devices Scope | Budget (Cr) | Expected Target Date
1 | HC2 | JMD J3 Steady State Security Systems | JMD | O2C | N | SITC of A,V | AKS | Completed | 959 | 906 | 4 | 69.33 | 2019-12-19
2 | HC52 | JMD J3 Steady State Security Systems - Gates and Tripods | JMD | O2C | N | SITC E | AKS | Completed | 0 | 140 | 181 | 10 | 2020-11-19
3 | HC64 | JMD - Admin Buildings - 5 nos | JMD | O2C | N | SITC A,V | AKS | Completed | 91 | 175 | 25 | 2.5 | 2019-04-19
4 | HC64 | JMD -CAB | JMD | O2C | N | SITC A,V | AKS | Pending | 16 | 22 | 6 | 2.5 | 2019-10-19
5 | HC72 | Automatic Gates at MTF & Haul Road | JMD | O2C | N | SITC E | AKS | Completed | 0 | 0 | 12 | 2.52 | 2019-05-19
6 | HC10 | JMD Upgrade Project – Personnel & Vehicle Tracking | JMD | O2C | N | SITC of PVTS | SKK/MB | Pending | 0 | 0 | 0 | 5 | TBD
7 | HC52 | Multi- Chemical Termi0ls - BRIBS and Biometric for Truck drivers | R&M | O2C | N | SITC BRIBS | SV | On Hold | 0 | 0 | 0 | 0.02
8 | HC58 | VCD - Biometric Access Control | VCD | O2C | N | SITC A | PM/GR | On Hold | 0 | 0 | 0 | 0.28
9 | HC61 | PMD – Plant Surveillance System | PMD | O2C | N | SITC V | PM/GR | Completed | 0 | 238 | 0 | 2.33 | 2019-07-01
10 | HC62 | NMD – Biometric Access Control | NMD | O2C | N | SITV A, V | GR | On Hold | 0 | 0 | 0 | 0.99 | 2019-07-01
11 | HC60 | R&M Warehouse, Cochin and Hubli | R&M | O2C | N | SITC of V | SV | On Hold | 0 | 0 | 0 | 0.15
12 | HC38 | CBM - Phase II, Security System | CBM | E&P | N | SITC A,V,E | SV | WIP | 20 | 104 | 0 | 10 | 2020-06-01
13 | HC66 | DMD, Township Video Surveillance system | DMD | O2C | N | SITC V | PM | On Hold | 0 | 0 | 0 | 0.2 | 2019-05-01
14 | HC47 | JNPT, Video Surveillance system Upgrade | JNPT | O2C | U | SITC V | PM | Completed | 0 | 8 | 0 | 0.1 | 2019-07-01
15 | CO3 | RCP Twin Tower | RCP | C&O | N | SITC of A,V,E | AP | WIP | 837 | 1601 | 60 | 29 | 2019-12-19
16 | CO12 | JWC (DAICEC) BKC | JWC | C&O | N | SITC of A,V,E | JD/GR | WIP | 1942 | 3203 | 710 | 230 | 2021-03-21
17 | CO42 | CISF, Accommodation- Retreat | RCP | C&O | N | SITC V | AP | Completed | 0 | 15 | 0 | 0.17 | 2019-04-19
18 | CO75 | Network 18_SRM | NW18 | C&O | N | SITC A,V & P | GR | Completed | 100 | 176 | 9 | 2.5 | 2019-06-01
19 | CO45 | RCP, Autozone | RCP | C&O | N | SITC A,V | AP | Completed | 3 | 10 | 0 | 0.08 | 2019-04-01
20 | CO80 | RCP, Temple | RCP | C&O | N | SITC V | AP | Completed | 0 | 10 | 0 | 0.11 | 2020-01-20
21 | CO82 | Reliance Foundation School, Jam0gar - Pilot | RFS-JMD | C&O | N | SITC V | AP/PM | Completed | 0 | 95 | 0 | 0.61 | 2019-05-01
22 | CO83 | Reliance Foundation School, Others | RFS-Others | C&O | N | SITC V | AP/GR | Completed | 0 | 300 | 0 | 3.06 | 2019-05-01
23 | CO84 | RCP, Automatic Number Plate Recognition System and Speed Detection | RCP | C&O | N | SITC V | AP | WIP | 0 | 39 | 0 | 2.77 | 2020-08-20
24 | CO86 | Reliance Foundation School, Koperkhairne - Ph II | RFS-KK | C&O | N | SITC V | AP/AT | Completed | 0 | 16 | 0 | 0.18 | 2019-04-01
25 | CO88 | BKC One | OneBKC | C&O | N | SITC | AS/GR | Completed | 37 | 53 | 0 | 0.7 | 2019-04-01
26 | CO59 | Seawind Bungalow | Seawind | Others | N | SITC V | AS | Completed | 0 | 27 | 0 | 0.15 | 2019-05-01
27 | CO93 | Man0t Bungalow | Mannat | Others | N | SITC A,V,P | AS | Completed | 0 | 0 | 0 | 1 | 2019-04-01
28 | CO94 | A1, Access Control upgrade | A1 | Others | U | SITC A | AS | WIP | 0 | 0 | 0 | 3 | 2019-04-01
29 | CO95 | RPL House Mumbai | RPL | C&O | U | SITC A,V | SV | Completed | 2 | 4 | 0 | 0.02 | 2019-06-01
30 | CO96 | IIT Delhi | IITD | C&O | U | SITC A,V | SV | Completed | 2 | 1 | 0 | 0.02 | 2019-05-01
31 | CO97 | Aurangzeb Guest House ,Delhi | Aurangzeb Guest House | C&O | U | SITC A,V | SV | Completed | 0 | 5 | 0 | 0.01 | 2019-05-01
32 | CO98 | Saffron Tower,Gujrat | Saffron Tower | C&O | U | SITC A,V | SV | Completed | 1 | 0 | 0 | 0.01 | 2019-05-01
33 | CO99 | Prer0 Arbour,Gujrat | Petro Harbour | C&O | U | SITC A,V | SV | Completed | 1 | 0 | 0 | 0.01 | 2019-05-01
34 | CO100 | 0vkar Office,Gujrat | Omkar Office | C&O | U | SITC A,V | SV | Completed | 1 | 1 | 0 | 0.02 | 2019-05-01
35 | CO101 | Dorairaj Tower,Tamil0du | Dorairaj Tower | C&O | U | SITC A,V | SV | Completed | 1 | 1 | 0 | 0.02 | 2019-05-01
36 | CO102 | RCP Phase 4 TC 22 Building Security System 7 the Floor | RCP | C&O | N | SITC of A,V | KB | WIP | 0 | 0 | 0 |  | 2020-05-20
37 | CO107 | RCP Robotics Warehouse | RCP | C&O | N | SITC of V | AP | Completed | 0 | 30 | 0 | 0.23 | 2020-02-20
38 | CO108 | RCP - A1 Warehouse | RCP | C&O | N | SITC of V | AP | WIP | 7 | 10 | 0 | 0.12 | 2020-08-20
39 | CO109 | DAKC - 2 Buildings | DAKC | C&O | N | SITC of V, A | AP | WIP | 88 | 235 | 0 | 1 | 2020-08-20
40 | CO110 | DALC - Expansions | DALC | C&O | N | SITC of V, A | SV | WIP | 27 | 66 | 0 | 0.4 | 2020-06-20
41 | CO111 | RFS - KK | RFS-KK | C&O | N | SITC of A | AP | WIP | 5 | 5 | 0 | 0.08 | 2020-08-20
42 | CO112 | RFS Schools | RFS-Others | C&O | N | SITC of A | PM | WIP | 12 | 0 | 0 | 0.07 | 2020-08-20
43 | CO113 | IDC -1 - Euronet to Genetec Migration | RCP | C&O | N | SITC of V, A | AP | WIP | 100 | 100 | 0 | 1.9 | 2020-12-31
44 | HC77 | R & M Sites - 2 nos | R&M | O2C | N | SITC of V, A | PM | WIP | 0 | 16 | 0 | 0.16 | 2020-08-20
45 | CO114 | RCP - Jio Controller Beta Roll Out | RCP | C&O | N | SITC of A | AP | Completed | 100 | 0 | 0 |  | 2020-03-20
46 | CO115 | Maker Euronet & Milestone Replacement (Controllers / Cameras / ARTs from JWC, JC SI WO) | Maker IV | C&O | N | SITC of V, A | SV | Completed | 57 | 153 | 0 | 6 | 2020-05-20
47 | CO116 | Genetec to replace Milestone, Verint, Euronet and HikVision VMS (Same IT Infra at JMD, RCP & Other Sites - Cameras) | Enterprise | Others | M | TC V | PM/AP | Completed | 0 | 2200 | 0 |  | 2019-12-19
48 | CO117 | RCP critical access control (Building Entry Fastlanes - 162) | RCP | C&O | N | SITC of A | AP | WIP | 0 | 0 | 162 | 0.62 | 2020-08-20
49 | HC78 | JMD access control replacement (1584 new controllers) | JMD | O2C | N | SITC of A | AKS | Completed | 1805 | 0 | 0 |  | 2020-04-20
50 | CO118 | Replacement of A0log Cameras to IP cameras | JMD | O2C | N | SITC of V | AKS | Completed | 0 | 140 | 0 |  | 2020-02-20
51 | CO119 | DAIS - New School (114 Doors, 314 Cameras, 16 Bollards, 2 KMS, 8 Scanners, 0.5km PIDS) | DAIS | C&O | N | SITC of A, V, PIDS | JD/GR | WIP | 114 | 314 | 24 |  | 2020-12-20
52 | HC79 | Manufacturing Sites - Access & Video Upgradation (426 Doors, 189 Cameras to be procured, Network Cabling) | Manufacturing Sites | O2C | N | SITC of V | PM | WIP | 0 | 0 | 0 |  | 2020-08-20
53 | HC80 | E&P Sites - Access & Video Upgradation (205 Doors, 288 cameras) | KGD6 | E&P | N | SITC of V | PM | WIP | 205 | 288 | 0 |  | 2020-06-20
54 | CO121 | A0log Camera Replacement | RCP | C&O | N | SITC of V | AP | WIP | 0 | 750 | 0 | 1.64 | 2020-12-20
55 | CO120 | DAIS School (25 Buses, 50 Cameras) | DAIS | C&O | N | SITC of V | AP | On Hold | 0 | 50 | 0 |  | TBD
56 | CO103 | IPL -19 | IPL | Others | N | SITC of V | AS | Completed | 0 | 10 | 0 | 0.2 | 2020-05-19
57 | CO104 | AGM - 19 | AGM | Others | N | SITC of V | AS | Completed | 0 | 5 | 0 | 0.1 | 2020-06-19
58 | HC81 | HMD - Olefins Control Room | HMD | O2C | N | SITC of A | PM | WIP | 4 | 0 | 0 | 0.02 | 2020-07-20
59 | HC82 | PMD - Process Control Rooms Access Control | PMD | O2C | N | SITC of A | PM | WIP | 8 | 0 | 0 |  | 2020-07-20
60 | CO105 | Sanpanda Office | Sanpada | C&O | N | SITC of A | PM/MB | WIP | 3 | 5 | 0 | 0.3 | 2020-07-20
61 | CO106 | Maker IV - 5th Floor Renovation | Maker IV | C&O | N | SITC of A | SV | WIP | 7 | 10 | 0 | 0.2 | 2020-06-20
62 | HC83 | VMD - DCS Rack Rooms | VMD | O2C | N | SITC of A | PM | WIP | 0 | 0 | 0 |  | 2020-08-20
63 | CO107 | Seven Hills Hospital | Seven Hills | Others | N | SITC of V | JD/GR | Completed | 0 | 27 | 0 | 0.15 | 2020-03-20